## Sheet1
Risk | Outcome | Responsibility | Impact | Likelihood | Risk Factor | Control/Mitigation | Response | Mitigated Impact | Mitigated Risk | Mitigated Risk Factor
User enters wrong id when prompted to update a domain class | Throws error and crashes app | Developer, User | 3 | 4 | 12 | Data Validation | Handling error and/or printing custom message within app | 1 | 4 | 4
Database connection drops | User unable to access or modify data | Developer, User | 4 | 1 | 4 | Use local connection, make backups of database | Re-establish connections | 3 | 1 | 3
Mistyping primitive wrappers | Compiler reads them as primitive types. Can cause crashes and errors. | Developer | 4 | 4 | 16 | Spellcheck | Update primitives to their reference type wrappers | 0 | 0 | 0
Creating unnecessary abstraction in the programme to adhere to principles | Creates multiple points of failure that can be hard to debug when the programme fails | Developer | 4 | 2 | 8 | Being sensibly lazy with abstraction and how code is structured | Rewriting the code to be simpler | 3 | 1 | 3
Overcomplicating Jira | Makes project hard to follow and hence code. Reduces efficiency and can reduce value created for clients. | Developer | 3 | 1 | 3 | Keeping user stories and tasks succinct and reducing unnecessary links | n/a | 1 | 1 | 1
Typing first letter of variables as capital letters | Calls class rather than method, or messes with class call, breaking programme | Developer | 4 | 4 | 16 | Spellcheck | Change variable style to Camel type | 4 | 0 | 0
Writing SQL query wrong in prepared statement | Yields error message and can crash programme. Date is not entered and may be forgotten | Developer | 4 | 4 | 16 | Spellcheck, Pre-writing SQL commands and testing them in SQL Editor before copying to prepared statement | Correct clerical errors, Rewrite SQL queries | 4 | 0 | 0
Updating Dependencies, but code isn't updated | Code just won't work, programme won't even compile | Developer | 5 | 2 | 10 | Comb through code after each update | Replace out of date code with updated code | 4 | 1 | 4
Entering duplicate keys when adding a new Order Item to an order | Item is not added as is duplicate | Developer | 2 | 2 | 4 | Create data validation to ensure duplicates cannot be entered | Develop solution. Close programme. | 2 | 0 | 0
LocalHost server does not have permissions to make changes or run. | Code will compile but no alterations can be made to database | Developer, System Admin, IT Team | 5 | 3 | 15 | Alter/Flush privileges. | Alter/Flush privileges and re-run. | 5 | 1 | 5
Tests are too specific | Working code fails tests | Developer | 2 | 4 | 8 | Spend more time on tests | Try to alter code/tests to make things work | 1 | 1 | 1